## Tabelle1
Function Point Calculation
1st semester
2nd semester
Because the UC “Take A Picture” is too huge and would make a defintive outliner, we decided to split it up into:
1. Implement Camera API 2: Train OCR Framework to read Handwriting 3: Process Picture (with OCR Framework) to extract Equation
The UC “Use Manual Calculator” is also split up:
1. Implement ANTLR Parser Generator 2: Define A Grammar that allows basic arithmetic Operations following Operator Precedence 3. Implement UserInterface 4. Implement SQLite Database and DB-Handler
UC | Documentation | Coding | Testing | DET | FTR/RET | Time spent (hours) | FP | Reason
Implement Camera API | 1 | 5 | 2 | 0 | 0 | 8 | 12.15 | Implementing the Camera into the Main Menu was the first UC, so it took us a while to get familiar with the IDE
Implement ANTLR Parser Generator | 8 | 10 | 3 | 0 |  | 21 | 25.22 | Implementing the Parser as a base for the Calculator Engine
Define A Grammar for Arithmetic Expressions | 3 | 10.5 | 4 | 0 | 0 | 17.5 | 26.19 | In order to get correct results, operator precedence must be working
Implement User Interface for Calculator | 0.5 | 1 | 0.5 | 0 | 0 | 2 | 7.2 | Input Equation and Display Results
Implement SQLITE Database and DB-Handler | 3 | 15 | 10 | 0 | 0 | 28 | 23 | A Database is needed to store results and pictures taken
View History | 0.5 | 5 | 2 | 0 | 0 | 7.5 | 8.25 | Talk to DB to retrieve entries, create new Activity
Delete Entry | 0.5 | 2 | 0.5 | 0 | 0 | 3 | 4.38 | Enable User to delete entries of previously calculated equations
Show Tour | 1 | 1.5 | 0.3 | 0 | 0 | 2.8 | 2.88 | Guide the User through the app on first startup
Train OCR Framework to read Handwriting | 10 | 25 | 20 | 0 | 0 | 55 | 40.56 | This Feature is not implemented yet, as it is definitely the most complex one. An AI is needed in order to extract usable Data from the picture.
Process Pictures to extract Equation | 5 | 10 | 3.5 | 0 | 0 | 18.5 | 25.11 | This Feature can only be implemented after the OCR Framework is functional and running