## Tabelle1
|  | Function Point Calculation | [6 empty] | "TinyTools" benutzen
1st semester
2nd semester
Because the UC “Take A Picture” is too huge and would make a defintive outliner, we decided to split it up into:
1. Implement Camera API 2: Train OCR Framework to read Handwriting 3: Process Picture (with OCR Framework) to extract Equation
The UC “Use Manual Calculator” is also split up:
1. Implement ANTLR Parser Generator 2: Define A Grammar that allows basic arithmetic Operations following Operator Precedence 3. Implement UserInterface 4. Implement SQLite Database and DB-Handler
UC | Documentation | Coding | Testing | DET | FTR/RET | Time spent (hours) | FP | Reason
Implement Camera API | 1 | 5 | 2 | 0 | 0 | 8 | 12.15 | Implementing the Camera into the Main Menu was the first UC, so it took us a while to get familiar with the IDE
Implement ANTLR Parser Generator | 8 | 11 | 3 | 0 |  | 22 | 25.22 | Implementing the Parser as a base for the Calculator Engine
Define A Grammar for Arithmetic Expressions | 3.5 | 13 | 4 | 0 | 0 | 20.5 | 26.19 | In order to get correct results, operator precedence must be working
Implement User Interface for Calculator | 1 | 2 | 0.5 | 0 | 0 | 3.5 | 7.2 | Input Equation and Display Results
Implement SQLITE Database and DB-Handler | 5 | 15 | 7 | 0 | 0 | 27 | 23 | A Database is needed to store results and pictures taken
View History | 0.5 | 5 | 2 | 0 | 0 | 7.5 | 8.25 | Talk to DB to retrieve entries, create new Activity
Delete Entry | 0.5 | 2 | 0.5 | 0 | 0 | 3 | 4.38 | Enable User to delete entries of previously calculated equations
Show Tour | 0 | 0 | 0 | 0 | 0 | 2.5 | 2.8 | Guide the User through the app on first startup
Call Mathpix API with http request | 0 | 0 | 0 | 0 | 0 | 18 | 20.56 | implement okhttp to talk with Mathpic API, create jason data to send as request
Process response data and error handling | 0 | 0 | 0 | 0 | 0 | 20 | 25.11 | parse response and handle it accordingly. If valid call interpreter and display result else shpw errormessage.