## Tabelle1
Identified | prob of occurrence | damage | mitgation strategy | person in charge | risk factor
can't find suitable framework | 30% | 10 | early testing | team | 3
lack of quality in OCR | 30% | 7 | early testing | team | 2.1
time management/projekt management | 25% | 9 |  | Sascha Hug | 2.25
inconsistent database for blog backups | 100% | 2 | redundancy | tobias Lamm | 2
|  | 28 |  |  | 9.35